## Feuil1
DESIGN | Done | Working | Not yet done | Bonuses
Objectif du 08/10/2014 | Author |  |  |  | Task | State
| Ludovic |  |  |  | Design Main Character (Paper)
Design Main Character (Vectoriel)
Design Main Character (Generic)
Position movement (Paper)
Hair design runing movement (Paper)
Generic construction for main character (vector)
Hair design runing movement (Vector)
| Romain |  |  |  | Design platform (paper)
Design platform (Vector)
Design Bumper (Paper)
Design Bumper (Vector)
Design Rope (Paper)
Design Rope (Vector)
| Yuxing |  |  |  | Design 2 enemies (Paper)
Design 2 enemies (Vector)
Design 2 enemies (Generic)
Objectif du 15/10/2014
| Ludovic |  |  |  | Hair design runing movement (Vector)
Hair design runing movement (Generic)
Runing movement (Paper)
Runing movement (Vector - Generic)
Jump movement (Paper)
Jump movement (Vector)
Slide movement (Paper)
Slide movement (Vector)
| Romain |  |  |  | Design Rope (Paper)
Design Rope (Vector)
Design bumper (Generic)
Design platform (Generic)
Background music 1 (Paper)
Background music 2 (Paper)
| Yuxing |  |  |  | Design 2 enemies (Vector)
Design 2 enemies (Generic)
Design collectible (Paper)
Design collectible (Vector)
Design collectible (Generic)
Design breakable (Paper)

## Feuil2
PROGRAMMATION | Fini | En cours | Pas fait | Bonus
Objectif du 08/10/2014 | Auteur |  |  |  | Tache | Objectif | Notes du chef de l'équipe
| Stanislas |  |  |  | Bases du moteur de jeu (saut, collisions) |  | N/A
Implementation de la caméra sur rails
Système de rotation de sprites
| Jerome |  |  |  | Implémentation du saut mural |  | RAS, Bon travail
Detection de collisions fines
| Kevin |  |  |  | Implementation des collectibles |  | Travail non rendu,
[5 empty] | Implementation du mouvement Glissade |  | 1er avertissement
Objectif du 15/10/2014