## Feuil1
DESIGN | Done | Working | Not yet done | Bonuses
Objectif du 08/10/2014 | Author |  |  |  | Task | State
| Ludovic |  |  |  | Design Main Character (Paper)
Design Main Character (Vectoriel)
Design Main Character (Generic)
Position movement (Paper)
Hair design runing movement (Paper)
Generic construction for main character (vector)
Hair design runing movement (Vector)
| Romain |  |  |  | Design platform (paper)
Design platform (Vector)
Design Bumper (Paper)
Design Bumper (Vector)
Design Rope (Paper)
Design Rope (Vector)
| Yuxing |  |  |  | Design 2 enemies (Paper)
Design 2 enemies (Vector)
Design 2 enemies (Generic)
Objectif du 15/10/2014
| Ludovic |  |  |  | Hair design runing movement (Vector)
Hair design runing movement (Generic)
Runing movement (Paper)
Runing movement (Vector - Generic)
Jump movement (Paper)
Jump movement (Vector)
Slide movement (Paper)
Slide movement (Vector)
| Romain |  |  |  | Design bumper (Generic)
Design platform (Generic)
Background music 1 (Paper)
Background music 2 (Paper)

## Feuil2
PROGRAMMATION
Date | Auteur | Objectif | Status
2014-10-08 | Stanislas | Bases du moteur de jeu (Saut, collisions basiques) | OK
|  | Création d'une caméra sur rails | OK
| Jerome | Gestion fine des collisions | OK
|  | Implementation du saut mural | OK
| Kevin | Implementation des collectibles | N/A
|  | Implementation du mouvement Glissade | N/A